## Sheet1
Sprint Backlog
Backlog Item | Story Points | Responsible | Status | Original Estimate | Day 21 | Day 22 | Day 23 | Day 24 | Day 25 | Day 28 | Day 29 | Day 30 | Day 1 | Pending 23 | Pending 24 | Pending 25 | Pending 28 | Pending 29 | Pending 30 | Pending 31 | Sprint Review
User Story #1 - View a 2 line report of game | 8
1.1 Extract dat from team (22/8/17) |  |  |  | 10
1.2 Create class / db model (23/8/17) |  |  |  | 5 | Day 22: 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4
1.3 Create MLB Serie Class (24/8/17) |  |  |  | 3 | Day 22: 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
Create MLB Game Class (24/8/17) |  |  |  | 3 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Day 21 to Day 1
User Story #2 - Series report by day | 1
2.1 . Align MLB Series per day (25/8/17) |  |  | Ezequiel says priority is to save in database | 8 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.2 Order schedule (26/8/17) |  |  | Ezequiel says priority is to save in database | 7 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
User Story #3 - Order series by sheets | 5 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.1 Creting of sheets depending of quantities and dates (27/8/17) |  |  | Ezequiel says priority is to save in database | 8 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
User Story #4 - Have info from MLB and Covers | 8 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Extract MLB Stats |  |  |  | 8 | Day 21: 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8
Extract MLB Schedule |  |  |  | 8 | Day 21: 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8
Extract MLB Series |  |  |  | 8 | Day 21: 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8
Extract Pitchers (21/8/17 - 22/8/17) | 8 |  |  | 8 | Day 21: 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8
Link between the extracted data (New requirement) | 8 |  | 8 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Day 21
User Story #5 - Fill data continuosly | 3 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5.1 Fill data periodically |  |  |  | 8 | [9 empty] | 8 | 8 | 4 | 0 | 0 | 0 | 0 | 8
5.2 Do upsert | [13 empty] | 0 | 0 | 2 | 2 | 0 | 2 | 2 | 0
5.3 Load game hour | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Extras 6. | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6.1 Extract datatable by headers | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6.2 Insert and alter Teams |  |  |  |  | Day 29: 2 |  |  |  |  | 2
6.3 Insert and alter Pitchers |  |  |  |  | Day 29: 2 |  |  |  |  | 2
6.2 Save data in database |  |  |  | 8 |  |  | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 8
Total |  |  | Actual remaining hours | 92 | 34 | 27 | 16 | 16 | 6 | 2 | 4 |  |  | 16 | 16 | 6 | 2 | 4 | 2 | 2 | 62
|  |  | Estimated remaining hours | 92 | 84 | 76 | 68 | 60 | 52 | 44 | 36 | 28 | 20