## Sprint1
Product Backlog Item | Task | Volunteer | Status | Original Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Sprint Review
As a user of DGS I need to use the system to insert start date, end date and on the system, also LogIdUser, so I can save a registry of these activities | Task 1 - Extract data from MLB Stats 8 HRS | Luis | Closed | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Task 2 - Extract series schedule | Luis | Closed | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Task 3. Extract actual standing | Luis | Closed | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Task 4 - Create github source | Luis | Closed | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | https://github.com/Luigig8per/CACtiveMQSubscribe
| Task 5 - Burn down chart creation | Luis | Closed | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Task 6 - Sprint retrospective | Luis | Closed | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Task 7 - Create View to insert data 1 a | Luis | Closed | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Its already working on desktop
| Task 8 - Create View to insert data 1 b | Luis | Closed | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Need to show the data on ASP.net
| Task 9 - Create View to insert data 1 c | Luis | Closed | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Task 10 - Create View to insert data 1 d | Luis | Closed | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Task 11 - Create View to insert data 1 e | Luis | Closed | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Task 12 - Sprint backlog creation | Luis | Closed | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Task 13 - Daily scrum | Luis | Closed | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Task 14 - Sprint review | Luis | Closed | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Task 15 - Sprint retrospective | Luis | Closed | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Task 16 - Sprint Planning | Luis | Closed | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Task 17 - Project Creation | Luis | Closed | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Total |  |  | 38 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Task 8 - Load leagues on cboBox |  |  | 2
| Task 9 - Load SP with leagues parameter |  |  | 2
| Task 10 - Extract to excel |  |  | 8
Task 19 - Load SP with Sport
| Task 20 - Load Exotics | 4 hrs
Sprint Goal | Task 21. Load Soccer and NBA w Definitive fields | 8 HRS
Some sprint goal | Task 22 - Load MLB Fields | 4 hs.
| 22.1 Load MLB Unidentified Fields | 4 hrs
23. MATCHUPS?
24. CANADIAN FOOTBALL
26. NFL FOOTBALL DIVISION
26.1 CANADIAN FOOTBALL DATA
26.5 General method for extract all data from some leagues