## Sheet1
Sprint Backlog Template
Backlog Item | Story Points | Responsible | Status | Original Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Sprint Review
User Story #1 - View a 2 line report of game | 8
1.1 Extract dat from team (22/8/17) |  |  |  | 10
1.2 Create class / db model (23/8/17) |  |  |  | 5
1.3 Create MLB Serie Class (24/8/17) |  |  |  | 3
Create MLB Game Class |  |  |  | 3
User Story #2 - Series report by day | 1
2.1 . Align MLB Series per day |  |  |  | 8
2.2 Order schedule |  |  |  | 7
User Story #3 - Order series by sheets | 5
3.1 Creting of sheets depending of quantities and dates |  |  |  | 8
User Story #4 - Have info from MLB and Covers | 8
Extract MLB Stats |  |  |  | 8 | Day 1: 8
Extract MLB Schedule |  |  |  | 8 | Day 1: 8
Extract MLB Series |  |  |  | 8 | Day 1: 8
Extract Pitchers (21/8/17 - 22/8/17) | 8 |  |  | 8 | Day 1: 4
User Story #5 - Fill data continuosly | 3
5.1 Fill data periodically |  |  |  | 8
Total |  |  | Total remaining hours | 84 | Day 1: 56; Day 2: 56
|  |  | Estimated remaining hours | 84 | 68 | 60 | 52 | 44 | 36 | 28 | 20 | 12 | 4
Create a Sprint Backlog in Smartsheet