## Sheet1
Backlog Item | Story Points | Responsible | Status | Proyected Estimate | Day 21 | Day 22 | Day 23 | Day 24 | Day 25 | Day 28 | Day 29 | Day 30 | Day 31 | Day 1 | Day 2 | Pending 25 | Pending 28 | Pending 29 | Pending 30 | Pending 31 | Sprint Review
Sprint Backlog
Backlog Item | Story Points | Responsible | Status | Proyected Estimate | Day 21 | Day 22 | Day 23 | Day 24 | Day 25 | Day 28 | Day 29 | Day 30 | Day 31 | Day 1 | Day 2 | Pending 25 | Pending 28 | Pending 29 | Pending 30 | Pending 31 | Sprint Review
User Story #1 - View a 2 line report of game | 8
1.1 Extract dat from team (22/8/17) |  |  |  | 10
1.2 Create class / db model (23/8/17) |  |  |  | 5 | Day 22: 4; Day 1: 0; Day 2: 0 | 0 | 0 | 0 | 0 | 0 | 4
1.3 Create MLB Serie Class (24/8/17) |  |  |  | 3 | Day 22: 2; Day 1: 0; Day 2: 0 | 0 | 0 | 0 | 0 | 0 | 2
Create MLB Game Class (24/8/17) |  |  |  | 3 | Day 22: 1; Day 1: 0; Day 2: 0 | 0 | 0 | 0 | 0 | 0
User Story #2 - Series report by day | 1
2.1 . Align MLB Series per day (25/8/17) |  |  | Ezequiel says priority is to save in database | 8 | Day 1: 0; Day 2: 0 | 0 | 0 | 0 | 0 | 0 | 0
2.2 Order schedule (26/8/17) |  |  | Ezequiel says priority is to save in database | 7 | Day 1: 0; Day 2: 0 | 0 | 0 | 0 | 0 | 0 | 0
2.3 Insert MLB Standings per day | 4 |  |  | 4 | Day 31: 4; Day 1: 0; Day 2: 0 | 0 | 0 | 0 | 0 | 0 | 4
2.4 Insert MLB | 4 |  |  | 4 | Day 31: 4; Day 1: 0; Day 2: 0 | 0 | 0 | 0 | 0 | 0 | 4
2.5 Link each game to standing of the day | 2 |  |  | 2 | Day 31: 2; Day 1: 0
2.5.6 To show each game standing on game table |  |  |  | 2 | Day 31: 2; Day 1: 0
2.5.6.1 To show each game standing on game in a understable way |  |  |  | 2 | Day 31: 2; Day 1: 0
|  |  |  | 2 | Day 31: 2; Day 1: 0
2.6 At start, To mark as notUpdated just the games of the days queried
User Story #3 - Order series by sheets | 5 |  |  |  | Day 1: 0; Day 2: 0 | 0 | 0 | 0 | 0 | 0 | 0
3.1 Creting of sheets depending of quantities and dates (27/8/17) |  |  | Ezequiel says priority is to save in database | 8 | Day 1: 0; Day 2: 0 | 0 | 0 | 0 | 0 | 0 | 8
[5 empty] | Day 1: 0; Day 2: 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | Day 1: 0; Day 2: 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | Day 1: 0; Day 2: 0 | 0 | 0 | 0 | 0 | 0 | 0
User Story #4 - Have info from MLB and Covers | 8 |  |  |  | Day 1: 0; Day 2: 0 | 0 | 0 | 0 | 0 | 0 | 0
Extract MLB Stats |  |  |  | 8 | Day 21: 8; Day 1: 0; Day 2: 0 | 0 | 0 | 0 | 0 | 0 | 8
Extract MLB Schedule |  |  |  | 8 | Day 21: 8; Day 1: 0; Day 2: 0 | 0 | 0 | 0 | 0 | 0 | 8
Extract MLB Series |  |  |  | 8 | Day 21: 8; Day 1: 0; Day 2: 0 | 0 | 0 | 0 | 0 | 0 | 8
Extract Pitchers (21/8/17 - 22/8/17) | 8 |  |  | 8 | Day 21: 4; Day 1: 0; Day 2: 0 | 0 | 0 | 0 | 0 | 0 | 8
Link between the extracted data (New requirement) | 8 |  | 8 |  | Day 1: 0; Day 2: 0 | 0 | 0 | 0 | 0 | 0 | 0
User Story #5 - Fill data continuosly | 3 |  |  |  | Day 1: 0; Day 2: 0 | 0 | 0 | 0 | 0 | 0 | 0
5.1 Fill data periodically |  |  |  | 8 | Day 1: 0; Day 2: 8 | 4 | 0 | 0 | 0 | 0 | 8
5.2 Do upsert |  |  |  |  | Day 1: 0; Day 2: 0 | 2 | 2 | 0 | 2 | 2 | 0
5.3 Load game hour |  |  |  |  | Day 1: 0; Day 2: 0 | 0 | 0 | 0 | 0 | 0 | 0
Extras 6. |  |  |  |  | Day 1: 0; Day 2: 0 | 0 | 0 | 0 | 0 | 0 | 0
6.1 Extract datatable by headers |  |  |  |  | Day 1: 0; Day 2: 0 | 0 | 0 | 0 | 0 | 0 | 0
6.2 Insert and alter Teams |  |  |  |  | Day 29: 2; Day 30: 0 |  |  | 2
6.3 Insert and alter Pitchers |  |  |  |  | Day 29: 2; Day 30: 0 |  |  | 2
Convert to console app |  |  | Cancelled as is not priority |  | Day 30: 2; Day 31: 0
1.4 Include Team Position |  |  |  |  | Day 30: 2; Day 31: 0
1.5 Tests on software |  |  |  | 2 | Day 30: 2; Day 31: 0
6.2 Save data in database |  |  |  | 8 |  |  | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 8
Actual remaining hours |  |  | Actual remaining hours | 110 | 42 | 35 | 0 | 0 | 6 | 2 | 4 | 6 | 16 | 0 | 0 | 6 | 2 | 4 | 2 | 2 | 70
Estimated remaining hours |  |  | Estimated remaining hours | 110 | 102 | 94 | 86 | 78 | 70 | 62 | 54 | 46 | 38 | 30 | 22 | 14 | 6 | -2 | -10 | -18